## 9-27-2022
Y | Pass / Fixed
Y | Fixed but other problems exist |  |  |  | Bundion Timelog System - Testing Schedule
N | Failed
ID | Test | [6 empty] | Expected behavior |  |  | Pass | Issue # | Result and notes
1 | New account
2 |  | Sign Up page | [5 empty] | Displays correctly |  |  | Y
3 |  |  | Validate form entries
4 |  |  |  | First Name |  |  |  | Required |  |  | Y
5 |  |  |  | Last Name |  |  |  | Required |  |  | Y
6 |  |  |  | Password |  |  |  | Required - only if both missing (otherwise match error) |  |  | Y
7 |  |  |  | Confirm
8 |  |  |  | Email |  |  |  | Required |  |  | Y
9 | [7 empty] | Unique |  |  | N |  | Reinstate and test
10 |  |  |  | Password and confirm |  |  |  | Must match |  |  | Y
11 |  |  |  | Account type |  |  |  | Set to Demonstration (Deadbeat after the Beta Promotion) |  |  | Y
12 |  |  | Create new account | [7 empty] | Y | #135 | Funky behaviour - error message shows if there was an error but isn't one, now.
13 |  |  |  | Entries added to the database
14 |  |  |  |  | accounts |  |  | Database entries created |  |  | Y
15 |  |  |  |  | companies | [5 empty] | Y
16 |  |  |  |  | company_accounts | [5 empty] | Y
17 |  |  |  |  | client (limit of 1) | [5 empty] | Y
18 |  |  |  |  | projects (limit of 1) | [5 empty] | Y
13 |  |  |  | Home page |  |  |  | User is automatically logged in and redirected to the home page |  |  | Y
19 | Existing Account
20 |  | Navigate to Sign In page | [5 empty] | Sign In page is displayed |  |  | Y
21 |  |  | Validate form entries
22 |  |  |  | Email |  |  |  | Required |  |  | Y
23 | [7 empty] | Unique |  |  | N |  | Reinstate and test
24 |  |  |  | Password |  |  |  | Required - only if both missing (otherwise match error) |  |  | Y
25 |  |  | Sign In |  |  |  |  | User is logged in |  |  | Y
26 |  | Select Menu Item: Clients | [5 empty] | User is taken to the "Clients" page |  |  | Y
27 | [7 empty] | Client menu item remains highlighted |  |  | N | #56
28 |  |  | Default Client |  |  |  |  | Client label is displayed |  |  | Y
29 | [7 empty] | Default client is displayed as text instead of a dropdown |  |  | Y
30 | [7 empty] | Client form is displayed |  |  | N | #136 | Deadbeat users can still edit the default account, they just can't create new clients.
31 |  |  |  | Client form |  |  |  | Default client name and description loaded |  |  | ??
32 |  |  |  | Save button |  |  |  | Updates the client in the database |  |  | ??
33 | [7 empty] | Updates the client selector default client name (still static) |  |  | ??
34 |  |  | Purchased Clients |  |  |  |  | Client dropdown is displayed |  |  | Y
35 | [7 empty] | Client dropdown defaults to "New client" |  |  | Y
36 |  |  |  | Create a new client |  |  |  | Client form is displayed |  |  | Y
37 | [7 empty] | Client name field is displayed |  |  | Y
38 | [7 empty] | Client description field is displayed |  |  | Y
39 | [7 empty] | Rate subform not shown (can bill required and false by default) |  |  | Y
40 |  |  |  |  | Enter a new client name, description and click "Save" |  |  | Client is saved to the database |  |  | N | #139 | Saving a client causes a javascript error. Since the error pertains to a fromCurrency call, it is probably because can_bill is set to false by default (it is a purchased option). Therefore, it is likely that this only fails for accounts that do not have the can_bill option.
41 | [7 empty] | Client dropdown is updated |  |  | N
42 | [7 empty] | New client is added to the list |  |  | N
43 | [7 empty] | New client is selected in the list |  |  | N
44 | [7 empty] | Delete button appears |  |  | N
45 |  |  |  | Edit an existing client |  |  |  | Client dropdown contains "New client" and a list of available clients |  |  | Y
46 |  |  |  |  | Select client from dropdown |  |  | Client form is populated with the selected client data |  |  | Y
47 | [7 empty] | Delete button appears if more than one client |  |  | Y | #103 | Delete button appears if there is only one client. Each account must have at least one client.
48 |  |  |  |  | Change the client name and description and click "Save" |  |  | Client is saved to the database |  |  | N | #139 | See 40-44
49 | [7 empty] | Client dropdown is updated |  |  | N
50 |  |  |  |  | Select "New Client" from the dropdown |  |  | The form is cleared |  |  | Y
51 | [7 empty] | The delete button disappears |  |  | Y
52 |  |  |  |  | Enter a new client name, description and click "Save" |  |  | Client is saved to the database |  |  | N | #139 | See 40-44
53 | [7 empty] | Client dropdown is updated |  |  | N
54 | [7 empty] | New client is added to the list |  |  | N
55 | [7 empty] | New client is selected in the list |  |  | N
56 | [7 empty] | Delete button appears |  |  | N
57 |  | Select Menu Item: Projects | [5 empty] | User is taken to the "Projects" page |  |  | Y
58 | [7 empty] | Project menu item remains highlighted |  |  | N | #56
59 | [7 empty] | Client label is displayed
60 |  |  | Single client |  |  |  |  | Default client is displayed for client instead of a dropdown
61 | [7 empty] | Project text (default project) or dropdown (purchased projects) is displayed
62 |  |  | Multiple clients |  |  |  |  | Clients sropdown list is displayed
63 | [7 empty] | "Select a client" is displayed as the header
64 | [7 empty] | Header is not selectable
65 | [7 empty] | Project dropdown list is not displayed
66 |  |  |  | Select a client from the list |  |  |  | Project text (default project) or dropdown (purchased projects) is displayed
67 |  |  | Client slots available |  |  |  |  | Client "New" button is displayed
68 | [7 empty] | Project label is not displayed
69 | [7 empty] | Project dropdown list is not displayed
70 |  |  |  | Client "New" button is clicked |  |  |  | Redirected to the "Clients" page
71 |  |  | Default project |  |  |  |  | Project label is displayed
72 | [7 empty] | Default project is displayed as text instead of a dropdown
73 | [7 empty] | Project form is displayed |  |  |  | #136 | Deadbeat users can still edit the default account, they just can't create new projects.
74 |  |  |  | Project form |  |  |  | Default project name loaded
Default project description loaded
75 |  |  |  | Save button |  |  |  | Updates the project in the database
76 | [7 empty] | Updates the project selector default project name (still static)
77 |  |  | Purchased projects |  |  |  |  | Project dropdown is displayed
78 | [7 empty] | Project dropdown defaults to "New project"
79 |  |  |  | Create a new project |  |  |  | Project form is displayed
80 | [7 empty] | Project name field is displayed
81 | [7 empty] | Project description field is displayed
82 | [7 empty] | Rate subform not shown (can bill required and false by default)
83 |  |  |  |  | Enter a new project name, description and click "Save" |  |  | Project is saved to the database |  |  |  | #139 | Probably the same issue as 40 - 44
84 | [7 empty] | Project dropdown is updated
85 | [7 empty] | New project is added to the list
86 | [7 empty] | New project is selected in the list
87 | [7 empty] | Delete button appears
88 |  |  |  | Edit an existing project |  |  |  | Project dropdown contains "New project" and a list of available projects
89 |  |  |  |  | Select client from dropdown |  |  | Project form is populated with the selected project data
90 | [7 empty] | Delete button appears if more than one project |  |  |  | #103 | Delete button appears if there is only one client. Each account must have at least one client.
91 |  |  |  |  | Change the project name and description and click "Save" |  |  | Project is saved to the database |  |  |  | #139 | See 83-87
92 | [7 empty] | Project dropdown is updated
93 |  |  |  |  | Select "New project" from the dropdown |  |  | The form is cleared
94 | [7 empty] | The delete button disappears
95 |  |  |  |  | Enter a new project name, description and click "Save" |  |  | Project is saved to the database |  |  |  | #139 | See 83-87
96 | [7 empty] | Project dropdown is updated
97 | [7 empty] | New project is added to the list
98 | [7 empty] | New project is selected in the list
99 | [7 empty] | Delete button appears
100 |  | Select Menu Item: Logging | [5 empty] | User is taken to the "Logging" page |  |  | Y
101 | [7 empty] | Project menu item remains highlighted |  |  | N | #56
102 | [7 empty] | Client label is displayed
Project label is not displayed
Neither project text (default project) nor dropdown (purchased projects) is displayed
[8 empty] | Logging form is not displayed |  |  | N
|  |  | No client slots available |  |  |  |  | "New" button is not displayed
|  |  | Client slots available |  |  |  |  | "New" button is displayed
|  |  | Single client |  |  |  |  | Client name is displayed as text
|  |  | Multiple clients |  |  |  |  | Client dropdown list is displayed
Header is selected
Header shows "Select a client"
|  |  |  | Select a client from the list |  |  |  | Project label is displayed
Project text (default project) or dropdown (purchased projects) is displayed
[5 empty] | No client slots available |  |  | "New" button is not displayed
[5 empty] | Client slots available |  |  | "New" button is displayed
[5 empty] | Single project |  |  | Project name is displayed as text
[5 empty] | Multiple projects |  |  | Project dropdown list is displayed
Header shows "Select a project"
Header is selected
|  |  |  | Select a project from the list |  |  |  | The "Start time" label is displayed
The start time is displayed in the format: weekday_name, month_name day_of_the_month, full_year hours: minutes meridian
The "Notes" label is displayed
The notes field is displayed
The log in button is displayed
|  |  | Edit option is set |  |  |  |  | See Options, below
The start time is a clickable link - on hover:
The start time is underlined
The cursor turns into a pointing hand
|  |  |  | Click the start time |  |  |  | The adjust date and time popup appears
|  |  |  | Date and time popup |  |  |  | The current date is selected
The current hour is selected
The current minute is selected
[8 empty] | The current meridian is selected |  |  | N
The popup is modal
Change the date
[5 empty] | Click the single greater-than sign on the calendar |  |  | The next month is selected
[5 empty] | Click the double greater-than signs on the calendar |  |  | The next year is selected
[5 empty] | Click the single less-than sign on the calendar |  |  | The pervious month is selected
[5 empty] | Click the double less-than signs on the calendar |  |  | The previous year is selected
[5 empty] | Click on a date |  |  | The start date is updated
[5 empty] | Click on the up pointer over the hours |  |  | The clock is updated
The start date is updated
[5 empty] | Click on the down pointer over the hours |  |  | The clock is updated
The start date is updated
[6 empty] | If the granularity is set to hourly |  | See Options, below
The minutes field is not displayed
The seconds field is not displayed
[7 empty] | Click on the up pointer over the hours | The clock is updated
The start date is updated
The increment counter increases by 1 returning to 1 after 12
[7 empty] | Click on the down pointer over the hours | The clock is updated
The start date is updated
The increment counter decreases by 1 returning to 12 after 1
[6 empty] | If the granularity is set to quarterly |  | See Options, below
The minutes field is displayed
The seconds field is not displayed
[7 empty] | Click on the up pointer over the hours | The clock is updated
The start date is updated
The increment counter increases by 1 returning to 1 after 12
[7 empty] | Click on the down pointer over the hours | The clock is updated
The start date is updated
The increment counter decreases by 1 returning to 12 after 1
[7 empty] | Click on the up pointer over the minutes | The clock is updated
The start date is updated
The increment counter increases by 15 returning to 0 after 45
[7 empty] | Click on the down pointer over the minutes | The clock is updated
The start date is updated
The increment counter decreases by 15 returning to 45 after 0
[7 empty] | Click the am meridian | The clock is updated
The start date is updated
The am button remains highlighted
[7 empty] | Click the pm meridian | The clock is updated
The start date is updated
The pm button remains highlighted
[6 empty] | If the granularity is set to minutely |  | See Options, below
The minutes field is displayed
The seconds field is not displayed
[7 empty] | Click on the up pointer over the hours | The clock is updated
The start date is updated
The increment counter increases by 1 returning to 1 after 12
[7 empty] | Click on the down pointer over the hours | The clock is updated
The start date is updated
The increment counter decreases by 1 returning to 12 after 1
[7 empty] | Click on the up pointer over the minutes | The clock is updated
The start date is updated
The increment counter increases by 1 returning to 0 after 59
[7 empty] | Click on the down pointer over the minutes | The clock is updated
The start date is updated
The increment counter decreases by 1 returning to 59 after 0
[7 empty] | Click the am meridian | The clock is updated
The start date is updated
The am button remains highlighted and the pm button loses its highlight
[7 empty] | Click the pm meridian | The clock is updated
The start date is updated
The pm button remains highlighted and the am button loses its highlight
[6 empty] | If the granularity is set to truetime |  | See Options, below
The minutes field is displayed
The seconds field is displayed
[7 empty] | Click on the up pointer over the hours | The clock is updated
The start date is updated
The increment counter increases by 1 returning to 1 after 12
[7 empty] | Click on the down pointer over the hours | The clock is updated
The start date is updated
The increment counter decreases by 1 returning to 12 after 1
[7 empty] | Click on the up pointer over the minutes | The clock is updated
The start date is updated
The increment counter increases by 1 returning to 0 after 59
[7 empty] | Click on the down pointer over the minutes | The clock is updated
The start date is updated
The increment counter decreases by 1 returning to 59 after 0
[7 empty] | Click on the up pointer over the seconds | The clock is updated
The start date is updated
The increment counter increases by 1 returning to 0 after 59
[7 empty] | Click on the down pointer over the seconds | The clock is updated
The start date is updated
The increment counter decreases by 1 returning to 59 after 0
[7 empty] | Click the am meridian | The clock is updated
The start date is updated
The am button remains highlighted and the pm button loses its highlight
[7 empty] | Click the pm meridian | The clock is updated
The start date is updated
The pm button remains highlighted and the am button loses its highlight
[7 empty] | Click the close button | The window closes
The selected date and time are displayed as the start date
|  |  | Click the "log in" button |  |  |  |  | The user is logged in
The client label is displayed
The client is shown as text
The project label is displayed
The project is shown as text
The "Start time" label is displayed
The start time is displayed in the format: weekday_name, month_name day_of_the_month, full_year hours: minutes meridian
The "End time" label is displayed
|  |  |  | End date is the same as the start date |  |  |  |  | The end time is displayed in the format: hours: minutes meridian
|  |  |  | End date is different from the start date |  |  |  |  | The end time is displayed in the format: weekday_name, month_name day_of_the_month, full_year hours: minutes meridian
|  |  |  | More than 8 hours has elapsed |  |  |  |  | The start and end times are shown in red
|  |  |  | Edit option is set |  |  |  |  | The start time is a clickable link - on hover:
The start time is underlined
The cursor turns into a pointing hand
The start time is displayed in the format: hours: minutes meridian
The end time is a clickable link - on hover:
The start time is underlined
The cursor turns into a pointing hand
|  |  | Click the start time |  |  |  |  | The Date and Time popup appears
|  |  | Change the date and time on the Date and Time popup |  |  |  |  | The start time changes accordingly
|  |  | Click the end time |  |  |  |  | The Date and Time popup appears
|  |  | Change the date and time on the Date and Time popup |  |  |  |  | The start time changes accordingly
Note on M15: Roger L. Main: Code exists - inactive until testing complete.
Note on M30: Roger L. Main: Code exists - inactive until testing complete.

## 9-9-2022
RMPC Timelog Testing Schedule
ID | Test |  |  |  |  | Expected Result |  | Test Result | Result Description
1 | Log in |  |  |  |  | User is logged in |  | Success
2 | Log out | [6 empty] | Failed
3 | Select Menu Item: Clients |  |  |  |  | User is taken to the "Clients" page |  |  |  | Fixed
[6 empty] | Client label is displayed |  |  |  | Success
4 |  | Default Client |  |  |  | "Default" is displayed for client instead of a dropdown |  |  |  | Failed
Client form is not displayed
5 |  | Purchased Clients |  |  |  | Client dropdown is displayed
Client form is displayed
Client dropdown defaults to "New client"
6 |  |  | No clients available |  |  | Client dropdown contains "New client" as the only option
7 |  |  |  | Enter a new client name and tab / click off of the field |  | Client is saved to the database
Client dropdown is updated
New client is added to the list
New client is selected in the list
[7 empty] | Delete button appears |  | No delete button appears
8 |  |  | Clients available |  |  | Client dropdown contains "New client" and a list of available clients
9 |  |  |  | Select client from dropdown |  | Client form is populated with the selected client data
Delete button appears
10 |  |  |  | Change the name of the client and tab / click off of the field |  | The client is saved and the dropdown is updated
11 |  |  |  | Select "New Client" from the dropdown |  | The form is cleared
The delete button disappears
12 |  |  |  | Enter a new client name and tab / click off of the field |  | Client is saved to the database
Client dropdown is updated
New client is added to the list
New client is selected in the list
[7 empty] | Delete button appears |  | No delete button appears
13 | Select Menu Item: Projects |  |  |  |  | User is taken to the "Projects" page
14 |  | Default Project |  |  |  | "Default" is displayed for client instead of a dropdown
Project list is automatically displayed
15 |  | Purchased Projects
16 |  |  | No clients available |  |  | Client label is displayed
[6 empty] | Client "New" button is displayed |  |  | Client dropdown is displayed
Project label is not displayed
[6 empty] | Project dropdown list is not displayed |  |  | Project dropdown is displayed
17 |  |  |  | Client "New" button is clicked |  | Redirected to the "Clients" page
18 |  |  | Clients available |  |  | Client label is displayed
Client dropdown is displayed
Client dropdown defaults to "Select a client"
Project label is not displayed
Project dropdown list is not displayed
19 |  |  |  | Select a client from the dropdown list |  | Project label is displayed
Project dropdown list is displayed
Project dropdown defaults to "New Project"
[6 empty] | Project form is displayed |  |  | No project form is displayed
20 |  |  |  |  | No projects available | Project "New" button is displayed
21 |  |  |  |  | Projects available
22
23
24
25
26
27
28
29
30
31

## Selectors
Page | Condition | Display | Showing | Works | Behaviour
Clients page | No clients | New client list header | Y | Y | blank form
| Has clients | New client list header | Y | Y | loads client into form
Projects page | No clients | New client button | Y | Y | new button
| Has clients | Select a client list header | Y | Y | shows project list
| No projects | New project list header | Y | Y | blank form
| Has projects | New project list header | Y | Y | loads project into form
Logging page | No clients | New client button | Y | Y | new button
| Has clients | Select a client list header | Y | Y | shows project list
| No projects | New project button | Y | Y | new button
| Has projects | Select a project list header |  |  | allows logging