## 9-27-2022
Y - Pass / Fixed
Y - Fixed but other problems exist | [5 empty] | RMPC Timelog Testing Schedule
N - Failed
ID | Test | [5 empty] | Behaviour | Pass | Issue # |  | Notes
1 | New account
2 |  | Sign Up page |  |  |  |  | Navigate | Y
3 |  | Validate form entries
4 |  |  | First Name |  |  |  | Required | Y | #3 |  | No error message transition
5 |  |  | Last Name |  |  |  | Required | Y
6 |  |  | Password |  |  |  | Required | Y
7 |  |  | Confirm |  |  |  | Required | Y
8 |  |  | Email |  |  |  | Required | Y | #2 | #3
9 | [6 empty] | Unique | N
10 |  |  | Password and confirm |  |  |  | Must match | Y | #3
11 |  |  | Account type |  |  |  | Set to Freelance | Y | #1 |  | Temporarily disabled pending end of Beta Promotion
12 |  | Create new account
13 |  |  | Home page |  |  |  | Navigate | N | #5 | #6 | Script error
14 |  |  | Database entries
15 |  |  |  | Accounts table |  |  | Create
16 | Existing Account
17 |  | Navigate to Sign In page |  |  |  |  | Sign In page is displayed | Y | #12 |  | User is returned to the sign up page
18 |  | Sign In |  |  |  |  | User is logged in
19 | Select Menu Item: Clients | [5 empty] | User is taken to the "Clients" page
20 | [6 empty] | Client label is displayed
21 |  | Default Client |  |  |  |  | "Default" is displayed for client instead of a dropdown
22 | [6 empty] | Client form is not displayed
23 |  | Purchased Clients |  |  |  |  | Client dropdown is displayed
24 | [6 empty] | Client form is displayed
25 | [6 empty] | Client dropdown defaults to "New client"
26 |  |  | No clients available |  |  |  | Client dropdown contains "New client" as the only option
27 |  |  |  | Enter a new client name and tab / click off of the field |  |  | Client is saved to the database
28 | [6 empty] | Client dropdown is updated
29 | [6 empty] | New client is added to the list
30 | [6 empty] | New client is selected in the list
31 | [6 empty] | Delete button appears |  |  |  | No delete button appears
32 |  |  | Clients available |  |  |  | Client dropdown contains "New client" and a list of available clients
33 |  |  |  | Select client from dropdown |  |  | Client form is populated with the selected client data
34 | [6 empty] | Delete button appears
35 |  |  |  | Change the name of the client and tab / click off of the field |  |  | The client is saved and the dropdown is updated
36 |  |  |  | Select "New Client" from the dropdown |  |  | The form is cleared
37 | [6 empty] | The delete button disappears
38 |  |  |  | Enter a new client name and tab / click off of the field |  |  | Client is saved to the database
39 | [6 empty] | Client dropdown is updated
40 | [6 empty] | New client is added to the list
41 | [6 empty] | New client is selected in the list
42 | [6 empty] | Delete button appears |  |  |  | No delete button appears
43 | Select Menu Item: Projects | [5 empty] | User is taken to the "Projects" page
44 |  | Default Project |  |  |  |  | "Default" is displayed for client instead of a dropdown
45 | [6 empty] | Project list is automatically displayed
46 |  | Purchased Projects
47 |  |  | No clients available |  |  |  | Client label is displayed
48 | [6 empty] | Client "New" button is displayed |  |  |  | Client dropdown is displayed
49 | [6 empty] | Project label is not displayed
50 | [6 empty] | Project dropdown list is not displayed |  |  |  | Project dropdown is displayed
51 |  |  |  | Client "New" button is clicked |  |  | Redirected to the "Clients" page
52 |  |  | Clients available |  |  |  | Client label is displayed
53 | [6 empty] | Client dropdown is displayed
54 | [6 empty] | Client dropdown defaults to "Select a client"
55 | [6 empty] | Project label is not displayed
56 | [6 empty] | Project dropdown list is not displayed
57 |  |  |  | Select a client from the dropdown list |  |  | Project label is displayed
58 | [6 empty] | Project dropdown list is displayed
59 | [6 empty] | Project dropdown defaults to "New Project"
60 | [6 empty] | Project form is displayed |  |  |  | No project form is displayed
61 |  |  |  |  | No projects available |  | Project "New" button is displayed
62 |  |  |  |  | Projects available
63
64
65
66
67
68
69
70
71
72

## 9-9-2022
RMPC Timelog Testing Schedule
ID | Test |  |  |  |  | Expected Result |  | Test Result | Result Description
1 | Log in |  |  |  |  | User is logged in |  | Success
2 | Log out | [6 empty] | Failed
3 | Select Menu Item: Clients |  |  |  |  | User is taken to the "Clients" page |  |  |  | Fixed
[6 empty] | Client label is displayed |  |  |  | Success
4 |  | Default Client |  |  |  | "Default" is displayed for client instead of a dropdown |  |  |  | Failed
Client form is not displayed
5 |  | Purchased Clients |  |  |  | Client dropdown is displayed
Client form is displayed
Client dropdown defaults to "New client"
6 |  |  | No clients available |  |  | Client dropdown contains "New client" as the only option
7 |  |  |  | Enter a new client name and tab / click off of the field |  | Client is saved to the database
Client dropdown is updated
New client is added to the list
New client is selected in the list
[7 empty] | Delete button appears |  | No delete button appears
8 |  |  | Clients available |  |  | Client dropdown contains "New client" and a list of available clients
9 |  |  |  | Select client from dropdown |  | Client form is populated with the selected client data
Delete button appears
10 |  |  |  | Change the name of the client and tab / click off of the field |  | The client is saved and the dropdown is updated
11 |  |  |  | Select "New Client" from the dropdown |  | The form is cleared
The delete button disappears
12 |  |  |  | Enter a new client name and tab / click off of the field |  | Client is saved to the database
Client dropdown is updated
New client is added to the list
New client is selected in the list
[7 empty] | Delete button appears |  | No delete button appears
13 | Select Menu Item: Projects |  |  |  |  | User is taken to the "Projects" page
14 |  | Default Project |  |  |  | "Default" is displayed for client instead of a dropdown
Project list is automatically displayed
15 |  | Purchased Projects
16 |  |  | No clients available |  |  | Client label is displayed
[6 empty] | Client "New" button is displayed |  |  | Client dropdown is displayed
Project label is not displayed
[6 empty] | Project dropdown list is not displayed |  |  | Project dropdown is displayed
17 |  |  |  | Client "New" button is clicked |  | Redirected to the "Clients" page
18 |  |  | Clients available |  |  | Client label is displayed
Client dropdown is displayed
Client dropdown defaults to "Select a client"
Project label is not displayed
Project dropdown list is not displayed
19 |  |  |  | Select a client from the dropdown list |  | Project label is displayed
Project dropdown list is displayed
Project dropdown defaults to "New Project"
[6 empty] | Project form is displayed |  |  | No project form is displayed
20 |  |  |  |  | No projects available | Project "New" button is displayed
21 |  |  |  |  | Projects available
22
23
24
25
26
27
28
29
30
31

## Selectors
Page | Condition | Display | Showing | Works | Behaviour
Clients page | No clients | New client list header | Y | Y | blank form
| Has clients | New client list header | Y | Y | loads client into form
Projects page | No clients | New client button | Y | Y | new button
| Has clients | Select a client list header | Y | Y | shows project list
| No projects | New project list header | Y | Y | blank form
| Has projects | New project list header | Y | Y | loads project into form
Logging page | No clients | New client button | Y | Y | new button
| Has clients | Select a client list header | Y | Y | shows project list
| No projects | New project button | Y | Y | new button
| Has projects | Select a project list header |  |  | allows logging